## Slide 1
The result was analyzed using research methodology, based on the finding of this study there are six major factors that causing time overrun in construction (delay) which are external factor, material and equipment factor, factor by contractor , factor by client, factor by consultant and labor factor.
Construction is the one of the largest industry. According to Riazi and Lamari (2013), project time overrun is one of the most significant problems with major concern at Malaysia. Project time overrun means non-completion project within specific duration as agreed in contract. The research question of this is to know the factors that contribute to delay and to find which is the highest.
ABSTRACT
INTRODUCTION
CONCLUSIONS AND RECOMMENDATION
Faculty of Industrial Management
THE SIGNIFICANT FACTORS CAUSING PROJECT TIME OVERRUN IN CONSTRUCTION AT TERENGGANU
Author : NURUL SYAKIRAH BINTI MOHD ALI
Bachelor of Project Management with Honors
This survey was conducted to find the factors causing time overrun (delay) from the contractors perspective. The objective of this study was to identify the factors and in order to rank the most influence factor. Sets of questionnaires are develop and data was collected by hand distributed and email. The scope of study focused on the construction project in Terengganu. The respondent of this study obtain from contractors registered under G7 with CIDB. The result of this study showed that the higher rate in delay come from external factor. External factor consist three subject such as weather condition, natural disaster and unavoidable disaster.
OBJECTIVES
RESULTS
METHODS
Subject Librarians guides to literature
Data collection Method
Data analysis method
SPSS
Likert Scale
Mean analysis
Conclusion and Recommendation
Final Report
Choose Topic
 | Factors | Average Mean | Rank
1 | External Factor Weather condition | 3.45 | 1
2 | Material and Equipment Factor Shortage of material and equipment | 3.35 | 2
3 | Contractor Factor Problem in planning and scheduling | 3.33 | 3
4 | Client Factor Delay in progress payment | 3.31 | 4
5 | Consultant Factor Lack of advance engineering software | 3.22 | 5
6 | Labor Factor Shortage of labor | 3.10 | 6
 | Total Average Mean | 3.29 | 
Research method is the technique to conduct a scientific research. For this study quantitative method is use. Quantitative method is refer to the statistical, mathematical or numerical data. The advantage of using quantitative because can using statistical software and required little duration to answer the questionnaire form.
Conclusion
From the result of this study, it can be conclude that the external factor such as weather condition, natural disaster (flood) and unavoidable disaster is the first major problem that causing time overrun in construction project at Terengganu.
Recommendation
Trough the study, there are some recommendation for future research :
Not limit the method. The method that can use such as interview and questionnaire for prevent returned question with not complete answer due to the limited time to answer question by respondent.
Expand the scope of study. The scope such as the cover of place and the number of population.
Research objectives are to determine the target of this research :
To identify the factors that causing to project time overrun
To rank the factors in contribute the most influenced factor of project time overrun